## Slide 1: Introduction

## Slide 2
Making a start on developing the biological pilar:
MRC “Developmental Pathway Funding Scheme”:
  https://www.ukri.org/opportunity/developmental-pathway-funding-scheme/
  A.Giacca, J.Parsons developing outline proposal
Need Biological Science CM …
MRes activity with Leo Cancer Care Ideas; still need to develop
08Feb23

## Slide 3
Vision firming up:
Proof-of-principle experiment proposed for PA2
  Discussion this afternoon
Concept for a parallel programme of experiments @ other sources
Pat Price developing stakeholder, comms, outreach and impact plans for PA2
MRes activity with Leo Cancer Care successful

## Slide 4
Waterfall chart from PA1 proposal …
 CM/12-month review to take stock of progress
 Formal element: check against milestones
✓
✓
✓
✓
✓
✓
12-month report
12-month report

## Slide 5: PA1 progress
Earned value:
  Arcane but useful …
In general:
  Tracking well:
  Comments:
    WP1: PMO
      “All” staff (OK)
    WP2: Source
      No spend reported first 4 months
      Recovering well
    WP3: Capture
      Recruitment issues
      Known problem, some of delays down to Home Office
    WP4: Ionacoustic
      Tracking well
      Some equipment spend to come
    WP5: End-station
      Tracking well
    WP6: Design & integration
      Tracking well
Preliminary!

## Slide 7: Visions Panel feedback
…
Proposal Feedback: Ion Therapy Research Facility (ITRF)
The Visions Panel found the ITRF proposal to provide evidence of the project’s potential to deliver of a step-change in capability and understood that such a facility would allow experimentation that does not currently exist elsewhere.
In terms of strategic drivers and the timeliness of the proposal within the current strategic landscape, the panel considered the proposal to be timely but felt that the proposal may benefit from clarifying the existing level of community support for the proposal. It was also noted that as the collaboration involved in the proposal is wide-reaching the proposal may benefit from including further information on the level of engagement from all members of the collaboration.
Please let us know if you have any queries.
Kind regards,
STFC Visions Team
… also discussing whether to revise the
“total infrastructure cost”.

## Slide 9: Timeline
Target for full programme definition mid Oct23

## Slide 10: Process document and progress
Updated following EB comments, shared with WPMs and LhARA collaboration, no further comments
Still awaiting comments from ITRF management
Shared with attendees at STFC Bid Review: 04Sep23

## Slide 11
https://ccap.hep.ph.ic.ac.uk/trac/raw-attachment/wiki/Research/LhARA/Documentation/TN/Governance/LhARA-Gov-Rev-2022-01.pdf

## Slide 12: PA2 detailed project plan
Rolling and formal reviews:
  Chris Townsley; STFC, RAL (PPD) Proj. Man. Off. has agreed to provide “rolling independent review” as we prepare the PA2 project plan
    On board; conversation with CT, Monday 18Sep23
  Mike Lamon (CERN Dir Acc. + Tech.) has agreed to organize second independent international review of PA2 programme:
    Will have greater focus on biomedical parts of programme than first review
    Will discuss with ML early October
    Target date for review Feb/Mar 2024